## ProjectTimeline
PROJECT TIMELINE PLANNER
{42}
| Project Start | 2022-02-05 |  |  | columns used to create the chart
CATEGORY | TASK | START | END | COLOR | Start | Blue | Red | Green | Brown | Orange | Purple
Request Raise | Problem statement | 2022-02-05 | 2022-05-05 | Blue | 2022-02-05 | 90 | 0 | 0 | 0 | 0 | 0
| Feasibility studies | 2017-01-15 | 2017-02-05 | Blue | 2017-01-15 | 22 | 0 | 0 | 0 | 0 | 0
| Rough Prototypes | 2017-02-06 | 2017-02-26 | Blue | 2017-02-06 | 21 | 0 | 0 | 0 | 0 | 0
System Design | Define design procedures | 2017-02-01 | 2017-02-15 | Red | 2017-02-01 | 0 | 15 | 0 | 0 | 0 | 0
| Refine Design | 2017-02-23 | 2017-03-05 | Red | 2017-02-23 | 0 | 11 | 0 | 0 | 0 | 0
System Prototyping | Design the prototypes | 2017-03-10 | 2017-04-09 | Green | 2017-03-10 | 0 | 0 | 31 | 0 | 0 | 0
| Acquire materials | 2017-03-10 | 2017-03-20 | Green | 2017-03-10 | 0 | 0 | 11 | 0 | 0 | 0
| Tooling | 2017-03-20 | 2017-04-09 | Green | 2017-03-20 | 0 | 0 | 21 | 0 | 0 | 0
| Quality Control Def. | 2017-04-10 | 2017-04-15 | Green | 2017-04-10 | 0 | 0 | 6 | 0 | 0 | 0
Systems deve | Application development | 2017-03-20 | 2017-04-04 | Brown | 2017-03-20 | 0 | 0 | 0 | 16 | 0 | 0
| Code review | 2017-03-20 | 2017-04-19 | Brown | 2017-03-20 | 0 | 0 | 0 | 31 | 0 | 0
| Refine Processes | 2017-04-05 | 2017-04-20 | Brown | 2017-04-05 | 0 | 0 | 0 | 16 | 0 | 0
Testing | Key Customers rqts | 2017-04-21 | 2017-04-26 | Orange | 2017-04-21 | 0 | 0 | 0 | 0 | 6 | 0
| Evaluate | 2017-04-21 | 2017-05-02 | Orange | 2017-04-21 | 0 | 0 | 0 | 0 | 12 | 0
Menteinance | Regular control | 2017-01-01 | 2017-02-28 | Purple | 2017-01-01 | 0 | 0 | 0 | 0 | 0 | 59
| Check version | 2017-01-01 | 2017-04-19 | Purple | 2017-01-01 | 0 | 0 | 0 | 0 | 0 | 109
| MILESTONE LABEL | DATE | Margin Bottom | Margin Top
| Milestone 1 | 2017-03-02 | 50% | 95%
| Milestone 2 | 2017-04-01 | 25% | 95%
| Milestone 3 | 2017-05-04 | 10% | 95%
| Milestone 4 |  | 30% | 95%
Formulas:
Start = IF(ISBLANK([START]),0,[START])