## WBS
Work Breakdown Structure | [5 empty] | LEGAL MANAGEMENT SYSTEM
| Project Start | 2022-04-25
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Phase 1
2 | 1.1 | Task Level 2 Customer Request | Business | 2022-05-02 | 2022-05-03 | Problem statement raise request
2 | 1.2 | Task Level2 Systems Analysis | Systems Analyst | 2022-05-04 | 2022-05-08 | All requirements definition
3 | 1.2.1 | Task Level3 Systems Design | Developers/System Analyst | 2022-05-09 | 2022-05-16 | Architecture specification
3 | 1.2.2 | Task Level3 Requirements sign off | Business/Analyst/Developers | 2022-05-17 | 2022-05-18 | End of phase 1
1 | 2 | Phase 2
2 | 2.1 | Task Level 2 Systems modelling and prototyping | UI/UX Designers | 2022-05-19 | 2022-05-26 | Visual designs of app pages
3 | 2.1.1 | Task Level 3 User Interface design | Business/Analyst/Developers/UI team | 2022-05-27 | 2022-05-28 | App blue printing
3 | 2.1.2 | Task Level 3 Systems development | Programmers/Software engineers | 2022-05-29 | 2022-06-13 | Actual development
1 | 3 | Phase 3
2 | 3.1 | Task Level 2 Systems testing | Unit/System testers | 2022-06-14 | 2022-06-17 | End to end system testing with use cases
3 | 3.1.1 | Task Level 3 Systems code-review | Unit/System testers/Engineers | 2022-06-18 | 2022-06-19 | review of test cases
4 | 3.1.1.1 | Task Level 4 Systems documentation | Software Engineers | 2022-06-20 | 2022-06-21 | manual write ups
2 | 3.2 | Task Level 2 Systems Handover | Software Engineers/Systems analyst | 2022-06-22 | 2022-06-23
3 | 3.2 | Task Level 3 Systems Mentainenance | Software Engineers/Systems analyst | Every 90 days | Ongoing